# I Morphometry BIRN: Annual NCRR Progress Report

## Cover Page

1. PHS Grant Number: U24 RR021382

2. Name of Recipient Institution: Massachusetts General Hospital

3. Reporting Period:

A. From - September 30, 2004

B. To - October, 2005

4. Principal Investigator:

A. Name:  Bruce Rosen, MD PhD

B. Title: Director, Athinoula A. Martinos Center for Biomedical Imaging

C. Telephone Number: 617-726-5122

D. Facsimile Number: 	617-726-7422

E. Electronic Mail Address: bruce@nmr.mgh.harvard.edu

## Contents

I Morphometry BIRN: Annual NCRR Progress Report	1

Cover Page	1

Contents	2

II Narrative Description	3

A Project Overview	3

B Project Focus	3

C October 2005 Progress Reports	4

C.1 Technology Developments	4

C.2 Application Tests	7

C.3 Collaborations	9

D  Outline of March 2006 and October 2006  goals	11

D.1 Technology Developments	11

D.2 Application Tests	13

E  Oct 04 – Oct 05 Publications	15

III Appendix	16

A Morphometry BIRN Core Projects proposed in Oct 2004 renewal	16

B Morphometry BIRN participants and roles	18

# II Narrative Description

## A Project Overview

The overall goal of the Morphometry BIRN (mBIRN) project is to develop, test and disseminate an infrastructure that enables a clinical research scientist to seamlessly acquire, share, analyze and mine multi-site data derived from structural MRI, diffusion MRI and clinical data, using processing and visualization tools developed at multiple sites. An excerpt from the October 2004 Competing Renewal Overall Narrative is included in the Appendix stating the Core Project goals (section A). The Appendix also includes a table (section B) that outlines the participating sites with their personnel and roles.

## B Project Focus

The goals of development, testing and dissemination define the focus of the mBIRN work:

Domains of Technology Development

- Standardized MRI acquisition protocols and image calibration methods for multi-site structural and diffusion imaging.

- Integration of visualization and morphometric analysis software developed at different sites to seamlessly interchange relevant data inputs and outputs. Software includes brain segmentation, shape analyses, diffusion analyses, integrated visualization, query atlas and machine learning tools.

- Computational informatics framework that enables curation, data management (raw MRI, derived morphometry data, clinical assessments, demographics) and computational workflows for a well-controlled way of generating and tracking provenance of derived data.

Prototype Application Tests

We have defined prototypical clinical research studies that require exactly those technologies we seek to develop. These prototype application tests use valuable, existing legacy data (neuroimaging and clinical) and/or software tools (visualization and morphometry) from multiple BIRN sites to address specific research issues in the study of ageing and Alzheimer’s Disease and Depression. Some application tests involve our non-BIRN Collaborators. These application cases enable validation of the technologies as well as dissemination by means of peer-reviewed publication of novel findings and methods that would not be possible without the BIRN (see section II.E).

Dissemination

#### The ultimate goal is to disseminate and support the validated technologies for the clinical research community. The BIRN recommendations for MRI acquisition protocols are posted on the mBIRN website. As much as possible software developments are based on standards and open source code. Completed software code will be distributed from the BIRN Portal and websites of the participating sites to enable tracking of the reach of the tools and infrastructure. Benchmark data sets (e.g. from the traveling human phantoms used in the MRI calibration studies) will be de-identified and made available to the scientific community for use in algorithm development.

## C October 2005 Progress Reports

Below are summary progress reports from the mBIRN projects.

### C.1 Technology Developments

Multi-site MRI acquisition and calibration methods

- Structural MRI Calibration

    - Reproducibility of T1-based multispectral data & derived morphometry (A. Dale, J. Jovicich)

      - Goals

      - Progress

    - Reproducibility of T2-based multispectral data & derived morphometry (J. MacFall, G. Gerig)

      - Goals

      - Progress

    - Calibration Code developments (S. Mori, A. Dale, J. Jovicich)

      - Goals

      - Progress

- Diffusion MRI Calibration

  - DTI Calibration Studies (S. Mori)

      - Goals

      - Progress

  - DTI distortion correction (EPI-based) (A. Song)

      - Goals

      - Progress

  - DTI distortion correction (post-acquisition) (S. Mori)

      - Goals

      - Progress

Analysis, Visualization and Interpretation Tools

- Segmentation Tools (B. Fischl, S. Pieper)

  - Protocol Specific Segmentation Methods (J. Jovicich)

  - Goals

  - Progress

  - Non-Protocol Specific Segmentation Methods (S. Pieper)

  - Goals

  - Progress

  - Manual brain subcortical segmentations (J. Jovicich)

  - Goals

  - Progress

  - Defacing (A. Bischoff-Grethe)

  - Goals

  - Progress

  - BIRNDUP (S. Pieper)

  - Goals

  - Progress

- Shape analysis Tools (A. Kolasny, S. Pieper)

- Goals

- Progress

- MRI Diffusion Tools (J. Fallon, S. Pieper)

- Goals

- Progress

- Visualization Tools (S. Pieper)

- Goals

- Progress

- Query Atlas (S. Pieper)

- Goals

- Progress

- Machine Learning Tools (P. Golland, T. Jaakkola, S. Pieper)

- Goals

- Progress

Computational Informatics

- Ontology (Christine Fennema-Notestine)

- Goals

- Progress

- Semantic Web (D. Karger, D. Kennedy)

- Goals

- Progress

- Database query and statistical analysis tools (Christine Fennema-Notestine, D. Kennedy)

- Goals

- Progress

- Processing Workflows (M. Mendis, H. Schmidt, S. Murphy)

- Goals

- Progress

- Data provenance (N. Aucoin)

- Goals

- Progress

- Morphometry BIRN data available to the public (D. Kennedy)

- Goals

- Progress

### C.2 Application Tests

Expand to include progress until end of Sept 2005

- Semi-Automated SHape Analysis (SASHA)

Background: The SASHA is a collaborative application aimed at developing a morphometry pipeline that integrates subcortical and shape analyses using tools developed at different sites. Clinical imaging data acquired at one site (WashU) is being analyzed by morphometry tools from two other different sites: Freesurfer subcortical segmentation at MGH followed by shape analysis (Large Deformation Diffeomorphic Metric Mapping, LDDMM) at JHU. A visualization tool from a fourth site (BWH) has been extended to enable the viewing of all the derived results on a single platform. To drive the integration of the pipeline preliminary data from R. Buckner (WashU) were analyzed (45 subjects: 21 nondemented controls, 18 very mild Alzheimer's Disease and 6 semantic dementia).

Progress: Main progress fronts include: i) preliminary validation of the SASHA pipeline for clinical diagnostic use, and ii) use of the Teragrid to facilitate computations and data handling originating from LDDMM analyses. These are outlined below.

- A novel statistical analysis method has been developed and tested that seems to provide accurate classification of subjects by disorders from LDDMM metric distances. These results are summarized in a Human Brain Mapping abstract (see section II.E)

- The TeraGrid (www.teragrid.org) computational resource was used to facilitate the LDDMM processing. The 32K cpu/hr processing time was distributed among 3 TeraGrid sites NCSA, CalTech and SDSC. Each site had local restrictions on the number of submissions to their resources. A meta-scheduler does not exist to submit all 4050 LDDMM jobs. Human intervention was needed to load, balance and monitor processing activities. Data results were automatically stored on BIRN repositories through the use of the Storage Resource Broker.

- Multi-Institutional Research in Analysis of Depression (MIRIAD)

Background: The MIRIAD is a collaborative application aimed at developing a morphometry pipeline that integrates multi-site neuroimaging analysis tools that process MRI data typically acquired for detecting white matter lesions (T2- and proton density MRI). To drive the application we attempted to extend the analysis of retrospective depression data from the Duke site, which had been previously analyzed using only manual segmentation methods. This data was further processed using registration, atlas generation and segmentation tools from the BWH and UCLA sites.

Progress: A first validation of the MIRIAD pipeline on the depression data has been completed and the results have been submitted as a manuscript (see abstract, III Appendix C).

- Multi-site Alzheimer’s Disease (MAD) project

Background:  It is expected that pooled analysis of multi-site data from prospectively collected data, such as that from the Alzheimer’s Disease Neuroimaging Initiative (ADNI, see II C.3. Collaborations section) will be successful since the acquisition and calibration methods will be tailored for this aim explicitly. However, many research groups have valuable legacy data sets that have been collected using best available methods for their site. This study will test the hypothesis that such legacy collections of clinical and structural MRI data from different sites can be meaningfully reanalyzed as a larger combined data set by using rigorous data curation and image analysis methods. We will explicitly test the hypotheses that hippocampal volume, as measured by the Freesurfer segmentation algorithm, will show the expected age related volume decrease, sex effect and laterality, as well as atrophy correlated with cognitive decline as measured by Mini-Mental Status Exam (MMSE) and diagnosis as measured by their Clinical Dementia Rating (CDR) score using data collected for studies of AD, Minimal Cognitive Impairment (MCI) and normal ageing at five mBIRN sites (UCSD, UCI, WashU and MGH/BWH combined).

Progress:  In the initial years of the mBIRN, the legacy data from the UCSD and MGH/BWH sites were used to develop a prototype demonstration while the image analysis software was being enhanced to work optimally on these legacy data sets. Enhancement of the analysis software required manual segmentation of representative data sets for the creation of a training atlas, improvements of the skull stripping and image registration algorithms as well as development of an algorithm to estimate total intracranial volume from the T1 images for normalization purposes. We have just completed the Freesurfer segmentation of over 280 total data sets from the contributing sites. Our preliminary analysis shows that the significant site difference in hippocampal volume in the healthy control subjects was a consequence of the variations in image processing which we have now eliminated.  Final data curation of the clinical data (age, sex, diagnosis, education, and MMSE score) and Freesurfer analysis results is now underway. (See http://www.na-mic.org/Wiki/index.php/Multi-site_AD for more details).

Of note, this study has been a key prototype for the development of the infrastructure for 1) data sharing across sites that followed federal HIPAA guidelines for de-identification (Defacing, BIRNDUP code), 2) common database schema for clinical and derived morphometry data at each site and a Mediator to bring the multi-site information together seamlessly (HID), 3) shared locations for data storage and retrieval (Storage Resource Broker), and 4) mediated queries that interrogate data contained in databases located at the two sites (HID Query Interface, 3Dslicer, Query Atlas).

- BIRN Effort to Localize Lesions (BELL)

Background:

Progress:

### C.3 Collaborations

The mBIRN is collaborating with multiple local and nation-wide projects. Besides our publications, these collaborations currently are the main method for disseminating and optimizing mBIRN tools and protocols.

Expand to include:

1) progress on the collaborations listed below until end of Sept 2005 and

2) progress on other active collaborations

- Alzheimer’s Disease Neuroimaging Initiative (ADNI, http://www.loni.ucla.edu/ADNI)

The ADNI is a multi-institutional effort to find neuroimaging and other biomarkers for the cognitive changes associated with Mild Cognitive Impairment and Alzheimer’s Disease. It is funded with the provision that all collected data must be shared with the broad research community, thus is closely aligned with the mBIRN goals and mission.

We collaborate closely with the ADNI Neuroimaging Core to support and assist them in their multi-site calibration of structural MRI data for brain morphometry. The acquisition protocols and correction methods that they are testing include those proposed by mBIRN, and will enable testing at over 40 sites. The evaluations of these methods on patients with MCI and AD will help establish the clinical relevance of the calibration methods.

- National Alliance for Medical Imaging Computing (NA-MIC, http://www.na-mic.org)

Supported by the NIH Roadmap Initiative for Bioinformatics and Computational Biology, NA-MIC is a multi-institutional, interdisciplinary team effort to develop novel algorithms and open source software engineering technologies for the analysis and visualization of medical image data. NA-MIC has central goals for training and dissemination of these tools to the medical research community.  Where BIRN’s emphasis has been on application and adaptation of existing image analysis techniques to a distributed grid-computing environment, NA-MIC participants are committed to extending the mathematical underpinnings of medical image analysis and converting these new techniques into deployable software solutions. In keeping with their distinct mandates, BIRN and NA-MIC collaborate closely on several fronts: i) data acquisition and analysis: both NA-MIC and mBIRN have key deliverables in the domain of DTI data.  MBIRN is providing key support to NA-MIC for acquisition, calibration and distortion correction methods, ii) data visualization: a key visualization software platform developed at the NA-MIC PI site, 3D Slicer, is being further developed under the auspices of both mBIRN and NA-MIC to vastly expand the capabilities of this versatile software tool, iii) BIRN is providing the secure data hosting facilities and Internet2 infrastructure to support the nationally distributed team of NA-MIC developers and end-users, iv) training and dissemination: members of the mBIRN MRI Calibration Core (A. Song from Duke, and S. Mori from JHU) have agreed to provide software tools and expertise to NA-MIC for development of educational materials (tutorials and other interactive, web based learning tools) for DTI data acquisition and data analysis. Further, the data collected by the mBIRN Calibration core will be made available for use in this educational material.

- Vietnam Era Twin Study of Aging (VETSA)

The VETSA is a multi-site (UCSD and MGH) longitudinal (5 year) study in which neuroimaging, neuropsychology, clinical assessments and genetic data is being collected from Vietnam-era (male-male) twins (n=300 pairs, half at each site) to study normal ageing.

Our collaborations with the VETSA project are two fold: i) the MRI acquisition protocols and correction methods used by VETSA include those proposed by mBIRN, so they will offer additional validation and optimization, and ii) the VETSA diffusion MRI data is being analyzed using software tools developed at mBIRN sites (white matter atlases generated by S. Mori at JHU and D. Kennedy at MGH, and also diffusion tensor registration tools from S. Pieper at BWH).

#### Function BIRN

The Morphometry and Function BIRN testbeds have worked together closely on several fronts, here we highlight just a few:

- High field morphometry calibration: mBIRN has performed the cortical and subcortical segmentations and surface reconstructions of sample structural MRI data acquired as part of fBIRN’s Phase II acquisitions in the Minnesota site (Siemens 3T). Qualitative inspection of the results shows that accurate segmentations were possible with the current acquisition protocol. The next step is to process high field sample data sets from the other fBIRN sites.

- Imaging genetics: Analysis efforts of imaging and genetics data have resulted in a paper in submission to Neuroinformatics (see section II E Publications). Dr. Smyth and Dr. Fallon are developing mathematical frameworks and neurocircuitry arguments, respectively, for datamining large datasets such as those being collated by mBIRN.

- BIRN-GCRC Interactions: Together with BIRN CC, GCRC and NCRR we have selected pilot short-term collaborative projects with three GCRCs. The main goal of these collaborative projects is to disseminate tools and experience in both directions. The GCRC’s are:

  - Medical College of Wisconsin (Steven Rao): this collaboration has two components: a) use of fBIRN’s stability assessment phantom, protocols and analysis tools at MCW and b) use of a rich fMRI dataset from MCW to drive fBIRN analysis tool development.

  - University of Texas (Peter Fox): this collaboration involves sharing and expanding the taxonomy for neuroimaging databases developed by both groups.

  - Brigham and Women’s Hospital (Gail Adler and Reisa Sperling): The collaboration with G. Adler is to enhance their cardiac image analysis tools using co-registration tools originally developed for brain applications. The collaboration with R. Sperling involves cross-site calibration of both functional and structural MRI for studies of AD.

## D  Outline of March 2006 and October 2006  goals

### D.1 Technology Developments

Multi-site MRI acquisition and calibration methods

- Structural MRI Calibration

    - Reproducibility of T1-based multispectral data & derived morphometry (A. Dale, J. Jovicich)

      - Goals March 2006

      - Goals October 2006

    - Reproducibility of T2-based multispectral data & derived morphometry (J. MacFall, G. Gerig)

      - Goals March 2006

      - Goals October 2006

    - Calibration Code developments (S. Mori, A. Dale, J. Jovicich)

      - Goals March 2006

      - Goals October 2006

- Diffusion MRI Calibration

  - DTI Calibration Studies (S. Mori)

      - Goals March 2006

      - Goals October 2006

  - DTI distortion correction (EPI-based) (A. Song)

      - Goals March 2006

      - Goals October 2006

  - DTI distortion correction (post-acquisition) (S. Mori)

      - Goals March 2006

      - Goals October 2006

Analysis, Visualization and Interpretation Tools

- Segmentation Tools (B. Fischl, S. Pieper)

  - Protocol Specific Segmentation Methods (J. Jovicich)

  - Goals March 2006

  - Goals October 2006

  - Non-Protocol Specific Segmentation Methods (S. Pieper)

  - Goals March 2006

  - Goals October 2006

  - Manual brain subcortical segmentations (J. Jovicich)

  - Goals March 2006

  - Goals October 2006

  - Defacing (A. Bischoff-Grethe)

  - Goals March 2006

  - Goals October 2006

  - BIRNDUP (S. Pieper)

  - Goals March 2006

  - Goals October 2006

- Shape analysis Tools (A. Kolasny, S. Pieper)

  - Goals March 2006

  - Goals October 2006

- MRI Diffusion Tools (J. Fallon, S. Pieper)

  - Goals March 2006

  - Goals October 2006

- Visualization Tools (S. Pieper)

  - Goals March 2006

  - Goals October 2006

- Query Atlas (S. Pieper)

  - Goals March 2006

  - Goals October 2006

- Machine Learning Tools (P. Golland, T. Jaakkola, S. Pieper)

  - Goals March 2006

  - Goals October 2006

Computational Informatics

- Ontology (Christine Fennema-Notestine)

  - Goals March 2006

  - Goals October 2006

- Semantic Web (D. Karger, D. Kennedy)

  - Goals March 2006

  - Goals October 2006

- Database query and statistical analysis tools (Christine Fennema-Notestine, D. Kennedy)

  - Goals March 2006

  - Goals October 2006

- Processing Workflows (M. Mendis, H. Schmidt, S. Murphy)

  - Goals March 2006

  - Goals October 2006

- Data provenance (N. Aucoin)

  - Goals March 2006

  - Goals October 2006

- Morphometry BIRN data available to the public (D. Kennedy)

  - Goals March 2006

  - Goals October 2006

### D.2 Application Tests

- Semi-Automated SHape Analysis (SASHA)

  - Goals March 2006

  - Goals October 2006

- Multi-Institutional Research in Analysis of Depression (MIRIAD)

  - Goals March 2006

  - Goals October 2006

- Multi-site Alzheimer’s Disease (MAD) project

  - Goals March 2006

  - Goals October 2006

- BIRN Effort to Localize Lesions (BELL) project

  - Goals March 2006

  - Goals October 2006

## E  Oct 04 – Oct 05 Publications

Below is a list of accepted and submitted publications in the report period. PDFs of the accepted publications can be found on the Morphometry BIRN wiki pages (http://www.na-mic.org/Wiki/index.php/Mbirn:_Recent_Publications). Abstracts of the submitted papers can be found in section III Apendix C.

#### Manuscripts

- Neu SC, Valentino DJ, Toga AW. The LONI Debabeler: a mediator for neuroimaging software. Neuroimage. 2005 Feb 15;24(4):1170-9

- Rex DE, Shattuck DW, Woods RP, Narr KL, Luders E, Rehm K, Stolzner SE, Rottenberg DA, Toga AW. A meta-algorithm for brain extraction in MRI. Neuroimage. 2004 Oct;23(2):625-37

- C Fennema-Notestine, IB Ozyurt, CP Clark, S Morris, A Bischoff-Grethe, MW Bondi, TL Jernigan, B Fischl, F Segonne, DW Shattuck, RM Leahy, DE Rex, AW Toga, KH Zou, the Morphometry BIRN and GG Brown.Quantitative Evaluation of Automated Skull-Stripping Methods Applied to Contemporary and Legacy Images: Effects of Diagnosis, Bias Correction and Slice Selection. Human Brain Mapping, 2005. (in press)

- B Chen, H Guo, AW Song.Fast Correction for Direction-Dependent Distortions in Diffusion Tensor Imaging Using Matched Magnetic Field Maps. (Submitted to NeuroImage)

- JR MacFall, WD Taylor, DE Rex, S Pieper, ME Payne, DR McQuoid, DC Steffens, R Kikinis, AW Toga,  RR Krishnan. Lobar Distribution Of Lesion Volumes In Late-Life Depression: Biomedical Informatics Research Network (BIRN). (Submitted to Archives of General Psychiatry)

- JA. Turner, P Smyth, JH. Fallon, F Macciardi, JL. Kennedy,  SG. Potkin, FIRST BIRN. Imaging phenotypes and genotypes in schizophrenia, 2005 (Submitted to Neuroinformatics).

#### Conference Abstracts

- J Jovicich, MF Beg, S Pieper, C Priebe, MM Miller, R Buckner, B Rosen, Morphometry BIRN. Biomedical Informatics Research Network: Integrating Multi-Site Neuroimaging Data Acquisition, Data Sharing and Brain Morphometric Processing . The 18th IEEE International Symposium on Computer-Based Medical Systems (IEEE CBMS 2005)

- B. Chen, H. Guo and AW. Song, Multi-directional distortion correction for DTI, International Society of Magnetic Resonance in Medicine, Miami May 2005

- J. Jovicich, S. Czanner, D. Greve, J. Pacheco, E Busa, A. van der Kouwe, Morphometry BIRN, B. Fischl., Test-retest reproducibility assessments for longitudinal studies: quantifying MRI system upgrade effects. International Society of Magnetic Resonance in Medicine, Miami May 2005

- M Faisal Beg, R Buckner, B Fischl, Y Park, E Ceyhan, C Priebe, C Ceritoglu, A Kolasny, T Brown, B Quinn, P Yu, B Gold, J. T Ratnanather, M Miller, BIRN Brain Morphometry. Pattern classification of hippocampal shape analysis in a study of Alzheimer's Disease, 2005 Human Brain Mapping Conference.

- X Han, J Jovicich, D Salat, A van der Kouwe, B Dickerson, D Rosas, N Makris, A Dale, B Fischl. CNR Comparison of three pulse sequences for structural MR Brain Imaging 2005 Human Brain Mapping Conference

- J Jovicich, S Czanner, B Quinn, J Pacheco, A van der Kouwe, PJ Snyder, M Analoui, M Albert, R Desikan, R Killiany, B Fischl, B Dickerson. Test-retest reliability assessment for longitudinal MRI studies: An intensity-based comparison of T1-weighted protocols and field strengths 2005 Human Brain Mapping Conference B Quinn, E Fenstermacher, X Han, J Pacheco, S Czanner, A van der Kouwe, P Maguire, D Raunig, M Albert, N Makris, R Desikan, R Killiany, B Dickerson, B Fischl. Test-retest reliability assessment for longitudinal MRI studies: A comparison of the effects of different T1-weighted protocols, scanner platforms, and field strengths on semi-automated hippocampal volume measures. 2005 Human Brain Mapping Conference

# III Appendix

## A Morphometry BIRN Core Projects proposed in Oct 2004 renewal

Specific Aims

The broadly defined mission of the NIH/NCRR funded Biomedical Informatics Research Network (BIRN- http://www.nbirn.net) project is to develop a scalable network of data acquisition techniques, databases and computational resources that can support the biomedical research enterprise. The Morphometry BIRN (mBIRN) test bed consortium project has initiated work to remove obstacles to the use of anatomically based biomedical imaging data as clinically relevant, quantitative biomarkers that are site and hardware independent. The mBIRN project has initiated the development and validation of image acquisition tools that are imaging platform independent, begun development of an integrated suite of image analysis tools from multiple BIRN partners to quantify these data in a variety of ways, and started to deploy robust data base structures that can store, retrieve, query and protect these complex imaging and associated metadata. These tools form the foundation of the mBIRN consortium, and are additionally being used as the anatomical basis set for the Functional Imaging Research Schizophrenia Test bed BIRN (FIRST BIRN) project.

In this competing renewal application, we propose three broad areas of work (Projects 1-3) to refine and expand upon our initial success: Project 1) optimization and validation of multi-site structural MRI acquisition and calibration methods, with extension to include additional imaging contrasts (T2 and DTI); Project 2) continued development of morphometric analysis, visualization, and interpretation tools; Project 3) continue the development of a neuroinformatics infrastructure that will deliver efficient data management, dynamic access, and application-based querying to neuroimaging data and the associated neuropsychiatric, behavioral and neurogenetic data. In the Clinical Collaboration section we propose our methods to propagate widespread application and use of the mBIRN infrastructure in support of an expanding set of clinical domains, using a phased approach. Finally, our Administrative Core section reviews our internal and external structures for coordinating the activities across our disparate sites, and discusses our plans to assure widespread dissemination of the mBIRN toolbox.

Specifically, we propose the following Projects, with their associated specific aims:

Project 1 Standardize and calibrate the acquisition of high-resolution structural MRI data to facilitate precise, quantitative, platform independent, multi-site evaluation of normal and pathological structural imaging data at multiple field strengths.

  - Develop methods to improve structural T1- and FSE-based PD, T2-weighted, and FLAIR weighted MRI acquisition protocols that maximize image quality, improve sensitivity, reduce noise and enable quantitative analysis of healthy and diseased tissue across sites and instruments.

  - Extend these methods to the acquisition of diffusion sensitive imaging, to improve diffusion MRI protocols and correction methods that minimize variability across sites while optimizing image quality and sensitivity for reconstructing fiber tracts and detecting abnormalities.

Project 2 Continue to develop, integrate and deploy a suite of freely available software to enable scientific investigation of the morphological bases of function and dysfunction through increasingly sophisticated image analysis on increasingly large subject populations acquired at multiple research sites.

2.1 Adapt and apply automated and semi-automated tools to segment subcortical structures, delineate the cortex, and parcellate cortical functional and anatomical regions from a range of input image protocols by drawing on expertise and existing software of the participating institutions.

2.2 Adapt and apply shape-based morphometric tools to investigate clinical and control populations: continue to develop interoperability between segmentation and shape analysis tools through standardized data representation.

2.3 Integrate Diffusion Tensor Imaging (DTI), anisotropy measurements, white matter (WM) atlases, and automated tractography techniques into the BIRN morphometry analysis infrastructure.

2.4 Provide an integrated visualization tool to support detailed investigation of morphometry and other data types.

2.5 Develop a visualization-based query tool to facilitate knowledge discovery and development of scientific explanations.

2.6 Adapt and apply machine-learning techniques to identify statistically related subpopulations of study subjects based on biomedical images.

Project 3 Create an infrastructure that will ensure efficient data management, reliable processing and dynamic access to imaging, behavioral, clinical and genetic data.

3.1  Continue to develop and deploy an extensible database, that can be adapted to fulfill a local site’s needs and that interoperates with the federated BIRN database infrastructure

3.2 Extend the BIRN infrastructure based on the capabilities and needs of the mBIRN collaborators to incorporate T2, FLAIR, and diffusion image data and genetic information.

3.3  Develop, test, and validate automated graphical protocols for data integration, pre- and post-processing and display.

Clinical Collaboration The goal is to propagate widespread application and use of the mBIRN infrastructure in an expanding set of clinical domains, using a phased approach. During the first phase of the renewal period collaborative projects will address questions directly in line with the broad clinical directions of the original mBIRN application – quantitative structural neuroimaging investigation of dementia and depression. This will first include sites with investigators already participating in mBIRN, but will subsequently be extended to include a broad array of sites through our collaboration with the new NIA Alzheimer’s Disease Neuroimaging Initiative (ADNI). In the second phase this effort will be expanded to include new areas of clinical investigation, outside of AD and depression, that require quantitative structural neuroimaging.  In the final phase we will identify new collaborators and implement new methods to support quantitative structural imaging.  Throughout, we propose to disseminate the tools and research resources of mBIRN to the broader scientific community through collaborations the NCRR funded General Clinical Research Centers (GCRCs) both locally and nationally, and through interactions with other national organizations, including the NIFTI program and the Radiological Society of North America, interested in utilizing BIRN resources to aid in studies within and outside the brain.

Administrative Core The mBIRN Administrative Core will be responsible for addressing the many and complex logistical, administrative, financial and ethical issues associated with the project and its new mandates. The proposed Administrative Core supports the efforts of Dr. Bruce Rosen, the overall mBIRN project PI, Dr. Jorge Jovicich, the mBIRN Project Manager, Monica Langone, who will manage the financial responsibilities, and Phyllis Somers, the clinical coordinator who will be responsible for administration of the human studies aspects of the project. The Core will provide support for the many working groups and both internal and external committees required to facilitate and coordinate the broad list of activities of this large and complex project.

Computational “Distributed Core” A distributed group of computer scientists and database experts will be assembled in a “virtual” manner, and includes investigators from the BIRN Coordinating Center (BIRN CC), and a group of investigators from MIT and the Partners Health Care System who are supported specifically by the mBIRN test bed, and who have expertise specifically required by the mBIRN Projects above.

## B Morphometry BIRN participants and roles

| Morphometry BIRN Personnel Budget | Brain Morphometry BIRN Sites and Roles |
| --- | --- |
|  | Funded Personnel | FTE | Roles |
| Administration Core MGH | B. Rosen J. Jovicich M. Langone P. Somers | 15% 100% 50% 30% | Principal Investigator Project Manager Administrative Assistant Administrative Assistant |
| Computation Core MGH | S. Murphy M. Mendis | 10% 100% | Co-Investigator (Workflows) Database Engineer (Workflows) |
| MGH Site Total MGH FTE | B. Rosen D. Kennedy R. Gollub B. Fischl P. Raines S. Czanner K. Teich H. Schmidt E. Busa A. vd Kouwe | 10% 20% 25% 5% 25% 100% 100% 100% 100% 5% 7.95 | Principal Investigator Site PI (Data Management Leader) Scientific Director Co-Investigator (MRI Calibration, Freesurfer optimization) Network Engineer Software Engineer (MRI Calibration) Software Engineer (Freesurfer optimization) Database Engineer (Data Management) Research Assistant (Freesurfer processing, quality assurance) MR Sequence Programmer (MRI Calibration) |
| BWH Site Total BWH FTE | R. Kikinis S. Pieper N. Aucoin T. Zlatnov W. Wells S. Warfield CF Westin K. Zou R. Estepar | 5% 20% 75% 15% 5% 5% 5% 5% 75% 2.10 | Site PI Co-Investigator (Analysis, Visualization & Interpretation Core leader) Software Engineer (Data Provenance) Network Engineer Co-Investigator (Protocol neutral segmentation developments) Co-Investigator (Protocol neutral segmentation optimization on MS data) Co-Investigator (Development and extensions of diffusion MRI modules in Slicer) Co-Investigator (statistical analysis support in multi-site MRI calibration) Postdoc (3D Slicer support for DTI applications) |
| MIT Site Total MIT FTE | E. Grimson P. Golland T. Jaakkola D. Karger S. Madden Karun Bakshi Mahnaz Maddah | 5% 5% 5% 5% 5% 100% 100% 2.25 | Site PI Co-Investigator (Machine Learning to analyze imaging metadata) Co-Investigator (Machine Learning to identify statistically related subpopulations) Co-Investigator (Semantic web tools for database management and retrieval tools) Co-Investigator (Database tools for semantic web applications) Research Assistant (Haystack project, semantic data mining) Research Assistant (Machine Learning in image context, classification, clustering) |
| WashU Site Total WashU FTE | R. Buckner D. Marcus S. Goldkind M. Ramaratnam TBD | 15% 80% 40% 100% 50% 2.60 | Site PI Co-Investigator (Data Management Tools) Computer Systems Manager Software Engineer (Data Management Tools) Software Engineer (Data Management Tools, dissemination to GCRC) |

| Morphometry BIRN Personnel Budget | Brain Morphometry BIRN Sites and Roles |
| --- | --- |
|  | Personnel | FTE | Roles |
| JHU Site Total JHU FTE | M. Miller A. Kolasny T. Brown S. Mori X. Xu K. Hua J. Morra | 0% 40% 100% 2% 100% 20% 50% 2.75 | Site PI Network Engineer (LDDMM/SRB/Teragrid developments) Database Engineer (LDDMM/SRB/Teragrid developments) Co-Investigator (co-lead multisite diffusion MRI calibration) Research Technician (MRI data acquisition and data management) Research data coordinator (MRI data analysis) Research Technician (extraction of Brainworks modules for applications in SASHA pipeline) |
| Duke Site Total Duke FTE | R. Krishnan J. MacFall A. Song F. Favaroni S. Gadde B. Boyd M. Payne TBD S. Rusincovitch | 5% 7.7% 5% 40% 66% 100% 25% 100% 100% 4.487 | Site PI Co-Investigator (lead data acquisition, analysis, calibration for lesion detection work) Co-Investigator (co-lead multisite diffusion MRI calibration) Analyst Programmer (local BIRN rack support) Analyst Programmer (computer support for DTI) Computer Programmer (software developer, data management, local GCRC liaison) Research Associate (IRB, assist/supervise lesion detection work) Postdoc Trainee (support for lesion detection analysis and DTI calibration) Data Technician |
| UCSD Site Total UCSD FTE | A. Dale L. Frank W. Kremen C. Notestine B. Ozyurt R. Notestine M. Perry TBD K. Lu | 20% 10% 20% 50% 50% 50% 100% 100% 35% 4.55 | Site PI Co-Investigator (support for multisite diffusion MRI calibration) Co-Investigator Co-Investigator (Ontology work, Multi-site AD application test) Database Engineer (HID developments) Software Engineer (support for MRI calibration) Research Assistant (support MRI calibration acquisition and analyses) System Administrator MR Sequence Programmer (support for multisite MRI calibration) |
| UCLA Site Total UCLA FTE | A. Toga K. Crawford I. Dos Santos R. Magsipoc S. Neu R. Nor | 3% 30% 75% 30% 40% 70% 2.48 | Site PI Database Manager (LONI database configuration, interface with users) Database Assistant (LONI database develoments) Network Administrator Knowledge Expert (LONI database develoments) Computer Programmer (LONI database statistical methods development) |
| UCI Site Total UCI FTE | S. Potkin P. Smyth J. Fallon D. Keator D. Wei S. Chen HJ Lee | 10% 10% 15% 40% 25% 32% 100% 2.32 | Site PI Computer Scientist Co-Investigator (White Matter Atlas generation and neuroscientist-friendly diffusion tools) Software Engineer Database Engineer Network Engineer Research Assistant |